## Sheet1
Sr No. | Short Bug Discription | Developer comment | Testing Team status
1 | Application generates Error page for specific data entered by user: | Done | Done
2 | Create contact: Application displays extra columns in report table as shown below for | AS per requirement | AS per requirement
3 | Application generates Error page for Create lead | Done | Done
4 | After creation of lead application not display back to lead list on right side of page as implemented for others. | Done | Done
5 | Create Enquiry generates Error page as follows: | Done | pending
6 | Need to change the hyperlink name(Back to display lead) as, it redirects to hotel enquiry page | Done | Done
7 | Application Displays tour enquiry link for Hotel user: | Done | Pending
8 | Create Quotation: Displays Amount=0 even amout is entered by user in form | Done | Done
9 | For creating Event from lead source when user click on “Add” evnet section , application rediret to a page where user again need to fill up the lead data | Done | Done
10 | Create New Event: Need to implement mandatory marks for all forms in application . | Done | Done
11 | VIEW: Enquiry - When user click on “View” enquiry link application redirect to “Create Quotation “, instead application redirect to enquriy page and show the hotel enquiry | AS per requirement | AS per requirement
12 | Could we maintain proper alignment for report tables. | Done | Done
13 | Inconsisteny in displaying the text messages: Some times application displays colorful messges and some times normally | Done | Not for create event-message displayed in bold letters. for Enquiry- messge displayed in formal text.
14 | Error page: when user try to Edit the event and click on “Update Event” | Done | Pending
15 | Application displays blank columns in generated Event report | AS per requirement | Pending- need to discuss
16 | Edit Event: application displays blank company name in edit mode | Done | Done (company name is removed from table)
17 | Create Company : Need to implement search crieteria for parent comapnay , after search which display his child companies list | Discussion is required | Discussion is required
18 | City master not found | Discussion is required | Pending
19 | Error page: Create company master generates error page when user enter data and click on “Add” button | Done | Done
20 | . Error page: Search company master generates error page when user enter text in contact field and click on search button. | Done | Done
21 | Wrong field name implementd for Search company master. Search field name should be “Company name”instead of Contact name. | Done | Done
22 | Space should be provided in word “Emailid” | Done | Done
23 | Found inconsistency in implenented menu names | Done | Done
24 | Application allows to create “Enquiry” for Lead status “Disqualified” . | Done | Pending
25 | Quotation pdf: Displays amount = 0 , as the quotation amount was already entered by user | Done | Done
26 | Event: for Event cancel status application allow to choose lead status: opportunity, and allow to update | Done
27 | Warning pop up messages: Need to implement proper validation messages with field names in pop up. Search lead: Need to implement proper validation messages with field names in pop up. Currently warning pop up messges appear without proper field names. | AS per requirement | AS per requirement
28 | Create Destination: Application not responds when user clicks on save button directly. | Done | Done
29 | Create Destination: when user selects “Destination” from drop down , then data appears as per selection, now press save button, data disappears. | Done | Done
30 | Add payment: warning message is not proper | Done | Done
31 | Add Payment: Payment receipt not display the submitted amount entered by user. | Done | Pending-currently generates error page
32 | Hotel login details displays – other menus such as “Agent master, Vendor master” | Discussion is required | Pending
33 | “FAQ” link generates server error. | Discussion is required | Pending
34 | “Target master” displays pop up messge “Duplicate data Found”, when user tries to enter second record. | AS per requirement | Pending
35 | . “Support” menu generates server error. When user click on “Reset password support” application generates server error. | Discussion is required | Pending
36 | Tour-APPLICATION GENERATES ERROR FOR HTML TAG WHEN USER ENTER THEM IN ITINERARY | Done
37 | Tour-FOR VERSION-2 , IF USER EDIT DATA FROM 5 TO 3 DAYS, TOUR DURATION, STILL APPLICAITON DISPLAYS 5 DAYS DATA IN VERSION 2
38 | Tour-Application allow to submit to sales, even operational user not put any data | Done
39 | Search lead is not working: as lead with name “Vishnu” is created, still application not displays the lead when user use search option | Done
40 | Hotel login displays tour data | Discussion is required
41 | Create Quotation links creates error page, for already created quaotation. | Done
42 | Once quoation is created, then again go to quotation page , by menuàcentral sales trackingà create hotel inquiryà back to hotel inquiry pageà click on create quotation link( where quotation is already created. | save as above Done
43 | Found two menu for create event | Done
44 | Once lead is created, application still displays contact person name on screen. Contact field should be blank once lead is created. | Discussion is required
45 | Back to lead: hyperlink redirects to search lead page: should be redirected or display created lead table When user click on back to lead, Redirects to following page | Discussion is required
46 | Application allows to create back dated events | Done
47 | Need to implement horizantal scrollbar for event list | Done
48 | Event list: Application displays “Start date” and “End Date” columns as blank. | AS per requirement
49 | Create enquiry: when user change the dropdown of “Query sub status” from “inprocess” to any other status say “confirmed”(you can select any), and again select the “Inprocess”, application not displays “sale amount” and “Sale date” field as shown. | Discussion is required
50 | Create Quotation: From create quotation page when user click on “Enquiry no” hyperlink, (for edit mode), application not displayes entered amount for “sale amoun” and date for “sale date” | Discussion is required
51 | Quotation pdf: Amount is not displayed in proper format. | Done
52 | Control should be properly implemented for “Hotel Enquiry” page. | Done
53 | When user click on “Back to hotel enquiry” hyperlink, application redirects “Create quotation” page as per requirement, but application auto select the lead name and screen displays “No record found” message. (By default lead name value should be “selected”) | Discussion is required
54 | Event: When user create event applicaition allow to enter some special characters as shown below, but while updating same data application displays warning pop up message “Special characters not allowed” | Discussion is required
55 | Need to implement mandatory marks for each form wherever required, here on “Create Enquiry” page.Where initially application does not display the mandatory marks, but when user click on “Save” button it displays warning messages about mandatroy fields. | Done
56 | Application allow to enter “0000000000” value in contact no. | Done
57 | Create company: when user tries to update by clicking on company name link (for edit mode),Application automatically selects the “parent company name “as displayed. | Done
58 | Error page generated for “Edit lead” section, when user change the status of lead. For following change from “Additional contact” to any and click on update. | Done
59 | Application allow to create enquiry for disqualified lead | Done
60 | Payment receipt pdf generate blank page when user click on pdf, as shown | Done
61 | Payment List: For payment status “in process” when user tries to edit by clicking on amont hyperlink as shown , application redirects to “Edit payment” page where application displays “Realisation date” in wrong format as (1/1/0001) with “Payment bounce reason” dropdown | Done